## Sheet1
[5 empty] | Report List |  |  | Issues that need to be solved
|  | No | Name | Status | Problem | Remarks | No | Name | Status | Date | Remarks
|  | 1 | Invoice | Done | No |  | 1 | Salse-->Dynamic Item Qty changes | Not Done
|  | 2 | Quotation | Done | No |  | 2 | Fixing thermal Printer Issue | Not Done
|  | 3 | Due Invoice (Sales--> Mange Invoice) | Done | No |  | 3 | Validation | Not Done
|  | 4 | Sales Report | Done | No |  | 4 | Adding Company Logo to the setting | Partial
|  | 5 | Item wise sels report | Done | No |  | 5 | Order Manage | Delete Order, Create Bill againts Purchase Invoice, See the short List of Product , Forcust the Product
|  | 6 | Profit Loss Report | Done | No
|  | 7 | Return Report | Done | No
|  | 8 | Currency Needs to added | Done | No
|  | 9 | Customer List Details | Done | No
|  | 10 | Employee List Report | Done | No | Image needs to be added
|  | 11 | Stock Report (Product) | Done | No
|  | 12 | Damage Report | Done | No
|  | 13 | Purchase_Invoice (Purchase) | Done | Yes | Few Invoices are not printing due to bad dataset
|  | 14 | Damage Report (Damage Entry) | No | Null
|  | 15 | Income Report (Income) | No | Null
Features we will Have in the POS
No. | Name
1 | POS Strrings
2 | Accountings
3 | Customers
4 | Suppliers
5 | Category
6 | Department
7 | Manage Damage
8 | Bar Code
9 | Employees
10 | Order
11 | Mangae Order
12 | Products
13 | Sales
14 | Damange Entry
15 | Income
16 | Expense
17 | Banking

## BarCode
No. | Name
Bar Code
Bar Code
|  | No | last Requirement | New Requirement | Status | Remarks | Date | Comments

## Sales
Sales
No. | Name | Description
Invoice
Quotation
Manage Invoice
Manage Quotation
Sales Return
Sales Report
Item wise Sales Report
Profit Loss
Return Report
[5 empty] | Invoice | [7 empty] | Quotation | [6 empty] | Manage Invoice | [6 empty] | Manage Quotation | [6 empty] | Sales Return | [6 empty] | Sales Report | [6 empty] | Item wise Sales Report | [6 empty] | Profit Loss | [6 empty] | Return Report
|  |  | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments

## Employee
Employee
No | Name | Description
Add Employee
Manage Employee
Employee Profile
Employee Access Right
|  |  |  | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments

## Order
Order
No. | Name
Add New Order
Order History
| Mange Order |  |  | Add New Order | [7 empty] | Order History | [6 empty] | Manage Order
|  | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments

## Damage
No | Name
1 | Damage Entry
2 | Damage Report
3 | Manage Damage
[5 empty] | Damage Entry | [6 empty] | Damage Report | [6 empty] | Manage Damage
|  | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments

## Income
No. | Name | Description
1 | Income Entry
2 | Income Category
[6 empty] | Income Entry | [6 empty] | Income Category
|  |  | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments

## Expens
No | Name | Description
Expense
Expense Category
[6 empty] | Expense | [6 empty] | Expense Category
|  |  | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments

## Banking
No | Name | Description
1 | Add New Bank Account
2 | Deposit
3 | Withdraw |  |  |  |  | Add New Bank Account | [6 empty] | Deposit | [6 empty] | Withdraw
|  |  | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments

## Product
No. | Name | Description
Add New Product
Bulk Update
Mange Product
Product List
Special Product
[6 empty] | Add New Product | [6 empty] | Bulk Update | [6 empty] | Mange Product | [6 empty] | Product List | [6 empty] | Special Product
|  |  | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments

## Category
No. | Name
Add Category
Add Category
|  | No | last Requirement | New Requirement | Status | Remarks | Date | Comments

## Department
No | Name
Add Department
Manage Department
[5 empty] | Add Departement | [6 empty] | Manage Departement
|  | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments

## Supplier
No | Name
1 | Add Supplier
2 | Manage Supplier
[5 empty] | Add Suppler | [6 empty] | Manage Supplier
|  | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments

## POS Settings
Features of Settings
No | Name | Description
1 | Settings
2 | Shop List
3 | Profile Page
4 | Add Task
5 | Task List |  |  |  |  | Settins | [6 empty] | Shop List | [6 empty] | Profile Page | [6 empty] | Add Task | [6 empty] | Task List
|  |  | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments

## Customer
No | Name
1 | Add Customer
2 | Manage Customer
[5 empty] | Add Customer | [6 empty] | Manae Customer
|  | No | last Requirement | New Requirement | Status | Remarks | Date | Comments | No | last Requirement | New Requirement | Status | Remarks | Date | Comments

## Accounts
Accounts Features
No. | Name
1 | Chart of Accounts
2
3
4
5 |  |  |  |  | Chart Accounts
|  | No | last Requirement | New Requirement | Status | Remarks | Date | Comments